## Proposal 1 WBS
Task ID | Task | Resource | Dependencies | Number of Resources | Duration (hrs) | Cost | Subtotal | Actual Weeks
1 | Phase 1: Pre-development activities | [5 empty] | 35672
1.1 | System requirements analysis |  |  |  |  | 2880 |  | 2.5
1.1.1 | Gather UI/UX requirements | Project Manager | - | 1 | 10 | 480
1.1.2 | Gather front-end development requirements | Project Manager | - | 1 | 10 | 480
1.1.3 | Gather database requirements | Project Manager | - | 1 | 10 | 480
1.1.4 | Gather service integration requirements | Project Manager | - | 1 | 10 | 480
1.1.5 | Finalize requirements | Project Manager | 1.1.1, 1.1.2, 1.1.3, 1.1.4 | 1 | 20 | 960
1.2 | Team Expansion |  |  |  |  | 7752 |  | 5
1.2.1 | Determine team requirements | HR Representative | 1.1.5 | 1 | 20 | 760
1.2.2 | Create job descriptions for open positions | HR Representative | 1.2.1 | 1 | 20 | 760
1.2.3 | Accept applications for new open positions | HR Representative | 1.2.2 | 1 | 40 | 1520
1.2.4 | Interview applicants - first round | HR Representative | 1.2.3 | 1 | 40 | 1520
1.2.5 | Interview applicants - second round | HR Representative | 1.2.4 | 1 | 40 | 1520
1.2.6 | Finalize offers | HR Representative | 1.2.5 | 1 | 20 | 760
1.2.7 | Onboard new hires | HR Representative | 1.2.6 | 1 | 24 | 912
1.3 | Training |  |  |  |  | 25040 |  | 1
1.3.1 | Training for existing employees | Technical Trainer, Sr. Developer, Jr. Developer I, Jr. Developer II | 1.2.7 | 4 | 40 | 25040
1.4 | Phase 1: Complete
2 | Phase 2: UI/UX Site Design | [5 empty] | 21744
2.1 | Create wireframes |  |  |  |  | 5472 |  | 4
2.1.1 | Develop wireframes for site designs | UI Designer | 1.3.1 | 1 | 80 | 2880
2.1.2 | Wireframe approvals (first round) | UI Designer | 2.1.1 | 1 | 16 | 576
2.1.3 | Wireframe updates | UI Designer | 2.1.2 | 1 | 40 | 1440
2.1.4 | Wireframe approvals (second round) | UI Designer | 2.1.3 | 1 | 16 | 576
2.2 | Develop site pages |  |  |  |  | 12960 |  | 9
2.2.1 | Develop product catalog page | UI Designer | 2.1.3 | 1 | 60 | 2160
2.2.2 | Develop individual product pages | UI Designer | 2.1.3 | 1 | 60 | 2160
2.2.3 | Develop customer review sections | UI Designer | 2.1.3 | 1 | 60 | 2160
2.2.4 | Develop customer account pages | UI Designer | 2.1.3 | 1 | 60 | 2160
2.2.5 | Develop cart and checkout pages | UI Designer | 2.1.3 | 1 | 60 | 2160
2.2.6 | Develop informational pages | UI Designer | 2.1.3 | 1 | 60 | 2160
2.3 | UI/UX Approvals |  |  |  |  | 3312 |  | 2.5
2.3.1 | UI/UX approvals (first round) | UI Designer | 2.2.1, 2.2.2, 2.2.3, 2.2.4, 2.2.5, 2.2.6 | 1 | 16 | 576
2.3.2 | UI/UX revisions | UI Designer | 2.3.1 | 1 | 60 | 2160
2.3.3 | UI/UX final approval | UI Designer | 2.3.2 | 1 | 16 | 576
2.4 | Phase 2: Complete
3 | Phase 3: Web application development | [5 empty] | 62856
3.1 | Develop product subsystem |  |  |  |  | 7440 |  | 2
3.1.1 | Build data schema for products | Sr. Developer | 1.1.5, 1.2.7 | 1 | 20 | 1200
3.1.2 | Build interface for product data | Sr. Developer | 3.1.1 | 1 | 60 | 3600
3.1.3 | Build API endpoints for products | Jr. Developer I | 3.1.1 | 1 | 40 | 1320
3.1.4 | Build business logic for products | Jr. Developer II | 3.1.1 | 1 | 40 | 1320
3.2 | Develop customer subsystem |  |  |  |  | 7440 |  | 3
3.2.1 | Build data schema for customer info | Sr. Developer | 1.1.5, 1.2.7 | 1 | 20 | 1200
3.2.2 | Build interface for customer data | Sr. Developer | 3.2.1 | 1 | 60 | 3600
3.2.3 | Build API endpoints for customer info | Jr. Developer I | 3.2.1 | 1 | 40 | 1320
3.2.4 | Build business logic for customer info | Jr. Developer II | 3.2.1 | 1 | 40 | 1320
3.3 | Develop pricing subsystem |  |  |  |  | 7440 |  | 3
3.3.1 | Build pricing data schema | Sr. Developer | 1.1.5, 1.2.7 | 1 | 20 | 1200
3.3.2 | Build interfacec for pricing data | Sr. Developer | 3.3.1 | 1 | 60 | 3600
3.3.3 | Build API endpoints for pricing | Jr. Developer I | 3.3.1 | 1 | 40 | 1320
3.3.4 | Build business logic for pricing | Jr. Developer II | 3.3.1 | 1 | 40 | 1320
3.4 | Develop transaction subsystem |  |  |  |  | 7440 |  | 3
3.4.1 | Build transaction data schema | Sr. Developer | 1.1.5, 1.2.7 | 1 | 20 | 1200
3.4.2 | Build interface for transaction data | Sr. Developer | 3.4.1 | 1 | 60 | 3600
3.4.3 | Build API endpoints for transactions | Jr. Developer I | 3.4.1 | 1 | 40 | 1320
3.4.4 | Build business logic for transactions | Jr. Developer II | 3.4.1 | 1 | 40 | 1320
3.5 | Develop product review subsystem |  |  |  |  | 7440 |  | 3
3.5.1 | Build review data schema | Sr. Developer | 1.1.5, 1.2.7 | 1 | 20 | 1200
3.5.2 | Build interface for review data | Sr. Developer | 3.5.1 | 1 | 60 | 3600
3.5.3 | Build API endpoints for product reviews | Jr. Developer I | 3.5.1 | 1 | 40 | 1320
3.5.4 | Build business logic for product reviews | Jr. Developer II | 3.5.1 | 1 | 40 | 1320
3.6 | Develop inventory management subsystem |  |  |  |  | 7440 |  | 3
3.6.1 | Build inventory management schema | Sr. Developer | 1.1.5, 1.2.7 | 1 | 20 | 1200
3.6.2 | Build interface for inventory management data | Sr. Developer | 3.6.1 | 1 | 60 | 3600
3.6.3 | Build API endpoints for inventory management | Jr. Developer I | 3.6.1 | 1 | 40 | 1320
3.6.4 | Build business logic for inventory management | Jr. Developer II | 3.6.1 | 1 | 40 | 1320
3.7 | Develop tax and shipping subsystem |  |  |  |  | 7440 |  | 3
3.7.1 | Build shipping and tax schema | Sr. Developer | 1.1.5, 1.2.7 | 1 | 20 | 1200
3.7.2 | Build interface for shipping and tax data | Sr. Developer | 3.7.1 | 1 | 60 | 3600
3.7.3 | Build API endpoints for shipping and tax processing | Jr. Developer I | 3.7.1 | 1 | 40 | 1320
3.7.4 | Build business logic for shipping and tax processing | Jr. Developer II | 3.7.1 | 1 | 40 | 1320
3.8 | Subsystem testing |  |  |  |  | 6600 |  | 2.5
3.8.1 | Integration testing | Tester I, Tester II | 3.1.1, 3.1.2, 3.1.3, 3.1.4, 3.2.1, 3.2.2, 3.2.3, 3.2.4, 3.3.1, 3.3.2, 3.3.3, 3.3.4, 3.4.1, 3.4.2, 3.4.3, 3.4.4, 3.5.1, 3.5.2, 3.5.3, 3.5.4, 3.6.1, 3.6.2, 3.6.3, 3.6.4, 3.7.1, 3.7.2, 3.7.3, 3.7.4 | 2 | 60 | 3960
3.8.2 | Acceptence testing | Tester I, Tester II | 3.8.1 | 2 | 40 | 2640
3.9 | System Approvals |  |  |  |  | 4176 |  | 2
3.9.1 | System approvals (first round) | Project Manager | 3.8.1, 3.8.2 | 1 | 16 | 768
3.9.2 | System revisions | Jr. Developer I, Jr. Developer II | 3.9.1 | 2 | 40 | 2640
3.9.3 | System final approval | Project Manager | 3.9.2 | 1 | 16 | 768
3.10 | Phase 3: Complete
4 | Phase 4: Deployment | [5 empty] | 1040
4.1 | Infrastructure |  |  |  |  | 800 |  | 0.5
4.1.1 | Build infrastructure | Infrastructure | 1.1.5 | 1 | 10 | 400
4.1.2 | Install required services | Infrastructure | 4.1.2 | 1 | 10 | 400
4.2 | Deploy website to infrastructure |  |  |  |  | 240 |  | 0.1
4.2.1 | Configure deployment pipelines | Sr. Developer | 4.1.2 | 1 | 2 | 120
4.2.2 | Deploy website | Sr. Developer | 4.2.1, 3.9.3 | 1 | 2 | 120
4.3 | Phase 4: Complete
5 | Phase 5: SalesForce integration | [5 empty] | 12720
5.1 | Develop data adapters |  |  |  |  | 4800 |  | 2
5.1.1 | Map customer data to SalesForce data | Sr. Developer | 3.2.4 | 1 | 40 | 2400
5.1.2 | Develop data conversion adapter | Sr. Developer | 5.1.1 | 1 | 40 | 2400
5.2 | Service integration |  |  |  |  | 5040 |  | 1
5.2.1 | Develop data egress to SalesForce | Jr. Developer I | 5.1.2 | 1 | 40 | 1320
5.2.2 | Develop data ingress from SalesForce | Jr. Developer II | 5.1.2 | 1 | 40 | 1320
5.2.3 | Develop data sync service | Sr. Developer | 5.1.2 | 1 | 40 | 2400
5.3 | SalesForce integration testing |  |  |  |  | 2640 |  | 1
5.3.1 | Test data egress | Tester I, Tester II | 5.2.3 | 2 | 20 | 1320
5.3.2 | Test data ingress | Tester I, Tester II | 5.3.1 | 2 | 20 | 1320
5.4 | SalesForce integration deployment |  |  |  |  | 240 |  | 0.1
5.4.1 | Cut-over to production customer data | Sr. Developer | 4.2.2 | 1 | 2 | 120
5.4.2 | Cut-over to production SalesForce instance | Sr. Developer | 5.3.2 | 1 | 2 | 120
5.5 | Phase 5: Complete
6 | Project Complete
TOTAL DURATION (CUMULATIVE HOURS) |  |  |  |  | 2768
ACTUAL DURATION (WEEKS) |  |  |  |  | 54
TOTAL COST | [6 empty] | 134032
Note on J1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: I estimated what the total of weeks of work (over lapping tasks, considering resources, and dependencies). I might wrap this into the WBS or hide the column.

## Proposal 1 Resources
Resource | Hourly | Weekly | FTE
Project Manager | 48 | 1923 | 100000
Sr. Developer | 60 | 2403 | 125000
Jr. Developer I | 33 | 1346 | 70000
Jr. Developer II | 33 | 1346 | 70000
UI Developer | 36 | 1442 | 75000
Infrastructure | 40 | 1634 | 85000
HR Representative | 38 | 1538 | 80000
Technical Trainer | 500 | 20000 | N/A
Tester I | 33 | 1346 | 70000
Tester II | 33 | 1346 | 70000

## P1 Loan
Loan Amount | 360800
Interest Rate (0.XX) | 0.08
Months | 60
Monthly Payment | 7315.72
Year | Beginning Balance | Payment | Principal | Interest | Cumulative Principal | Cumulative Interest | Ending Balance
1 | 360800 | 87788.64 | 61133.95 | 26654.69 | 61133.95 | 26654.69 | 299666.05
2 | 299666.05 | 87788.64 | 66208.05 | 21580.59 | 127342 | 48235.28 | 233458
3 | 233458 | 87788.64 | 71703.27 | 16085.37 | 199045.27 | 64320.65 | 161754.73
4 | 161754.73 | 87788.64 | 77654.63 | 10134.01 | 276699.9 | 74454.66 | 84100.1
5 | 84100.1 | 87788.64 | 84099.9 | 3688.74 | 360799.8 | 78143.4 | 0.2
Month | Beginning Balance | Payment | Principal | Interest | Cumulative Principal | Cumulative Interest | Ending Balance
1 | 360800 | 7315.72 | 4910.39 | 2405.33 | 4910.39 | 2405.33 | 355889.61
2 | 355889.61 | 7315.72 | 4943.12 | 2372.6 | 9853.51 | 4777.93 | 350946.49
3 | 350946.49 | 7315.72 | 4976.08 | 2339.64 | 14829.59 | 7117.57 | 345970.41
4 | 345970.41 | 7315.72 | 5009.25 | 2306.47 | 19838.84 | 9424.04 | 340961.16
5 | 340961.16 | 7315.72 | 5042.65 | 2273.07 | 24881.49 | 11697.11 | 335918.51
6 | 335918.51 | 7315.72 | 5076.26 | 2239.46 | 29957.75 | 13936.57 | 330842.25
7 | 330842.25 | 7315.72 | 5110.1 | 2205.62 | 35067.85 | 16142.19 | 325732.15
8 | 325732.15 | 7315.72 | 5144.17 | 2171.55 | 40212.02 | 18313.74 | 320587.98
9 | 320587.98 | 7315.72 | 5178.47 | 2137.25 | 45390.49 | 20450.99 | 315409.51
10 | 315409.51 | 7315.72 | 5212.99 | 2102.73 | 50603.48 | 22553.72 | 310196.52
11 | 310196.52 | 7315.72 | 5247.74 | 2067.98 | 55851.22 | 24621.7 | 304948.78
12 | 304948.78 | 7315.72 | 5282.73 | 2032.99 | 61133.95 | 26654.69 | 299666.05
13 | 299666.05 | 7315.72 | 5317.95 | 1997.77 | 66451.9 | 28652.46 | 294348.1
14 | 294348.1 | 7315.72 | 5353.4 | 1962.32 | 71805.3 | 30614.78 | 288994.7
15 | 288994.7 | 7315.72 | 5389.09 | 1926.63 | 77194.39 | 32541.41 | 283605.61
16 | 283605.61 | 7315.72 | 5425.02 | 1890.7 | 82619.41 | 34432.11 | 278180.59
17 | 278180.59 | 7315.72 | 5461.18 | 1854.54 | 88080.59 | 36286.65 | 272719.41
18 | 272719.41 | 7315.72 | 5497.59 | 1818.13 | 93578.18 | 38104.78 | 267221.82
19 | 267221.82 | 7315.72 | 5534.24 | 1781.48 | 99112.42 | 39886.26 | 261687.58
20 | 261687.58 | 7315.72 | 5571.14 | 1744.58 | 104683.56 | 41630.84 | 256116.44
21 | 256116.44 | 7315.72 | 5608.28 | 1707.44 | 110291.84 | 43338.28 | 250508.16
22 | 250508.16 | 7315.72 | 5645.67 | 1670.05 | 115937.51 | 45008.33 | 244862.49
23 | 244862.49 | 7315.72 | 5683.3 | 1632.42 | 121620.81 | 46640.75 | 239179.19
24 | 239179.19 | 7315.72 | 5721.19 | 1594.53 | 127342 | 48235.28 | 233458
25 | 233458 | 7315.72 | 5759.33 | 1556.39 | 133101.33 | 49791.67 | 227698.67
26 | 227698.67 | 7315.72 | 5797.73 | 1517.99 | 138899.06 | 51309.66 | 221900.94
27 | 221900.94 | 7315.72 | 5836.38 | 1479.34 | 144735.44 | 52789 | 216064.56
28 | 216064.56 | 7315.72 | 5875.29 | 1440.43 | 150610.73 | 54229.43 | 210189.27
29 | 210189.27 | 7315.72 | 5914.46 | 1401.26 | 156525.19 | 55630.69 | 204274.81
30 | 204274.81 | 7315.72 | 5953.89 | 1361.83 | 162479.08 | 56992.52 | 198320.92
31 | 198320.92 | 7315.72 | 5993.58 | 1322.14 | 168472.66 | 58314.66 | 192327.34
32 | 192327.34 | 7315.72 | 6033.54 | 1282.18 | 174506.2 | 59596.84 | 186293.8
33 | 186293.8 | 7315.72 | 6073.76 | 1241.96 | 180579.96 | 60838.8 | 180220.04
34 | 180220.04 | 7315.72 | 6114.25 | 1201.47 | 186694.21 | 62040.27 | 174105.79
35 | 174105.79 | 7315.72 | 6155.01 | 1160.71 | 192849.22 | 63200.98 | 167950.78
36 | 167950.78 | 7315.72 | 6196.05 | 1119.67 | 199045.27 | 64320.65 | 161754.73
37 | 161754.73 | 7315.72 | 6237.36 | 1078.36 | 205282.63 | 65399.01 | 155517.37
38 | 155517.37 | 7315.72 | 6278.94 | 1036.78 | 211561.57 | 66435.79 | 149238.43
39 | 149238.43 | 7315.72 | 6320.8 | 994.92 | 217882.37 | 67430.71 | 142917.63
40 | 142917.63 | 7315.72 | 6362.94 | 952.78 | 224245.31 | 68383.49 | 136554.69
41 | 136554.69 | 7315.72 | 6405.36 | 910.36 | 230650.67 | 69293.85 | 130149.33
42 | 130149.33 | 7315.72 | 6448.06 | 867.66 | 237098.73 | 70161.51 | 123701.27
43 | 123701.27 | 7315.72 | 6491.04 | 824.68 | 243589.77 | 70986.19 | 117210.23
44 | 117210.23 | 7315.72 | 6534.32 | 781.4 | 250124.09 | 71767.59 | 110675.91
45 | 110675.91 | 7315.72 | 6577.88 | 737.84 | 256701.97 | 72505.43 | 104098.03
46 | 104098.03 | 7315.72 | 6621.73 | 693.99 | 263323.7 | 73199.42 | 97476.3
47 | 97476.3 | 7315.72 | 6665.88 | 649.84 | 269989.58 | 73849.26 | 90810.42
48 | 90810.42 | 7315.72 | 6710.32 | 605.4 | 276699.9 | 74454.66 | 84100.1
49 | 84100.1 | 7315.72 | 6755.05 | 560.67 | 283454.95 | 75015.33 | 77345.05
50 | 77345.05 | 7315.72 | 6800.09 | 515.63 | 290255.04 | 75530.96 | 70544.96
51 | 70544.96 | 7315.72 | 6845.42 | 470.3 | 297100.46 | 76001.26 | 63699.54
52 | 63699.54 | 7315.72 | 6891.06 | 424.66 | 303991.52 | 76425.92 | 56808.48
53 | 56808.48 | 7315.72 | 6937 | 378.72 | 310928.52 | 76804.64 | 49871.48
54 | 49871.48 | 7315.72 | 6983.24 | 332.48 | 317911.76 | 77137.12 | 42888.24
55 | 42888.24 | 7315.72 | 7029.8 | 285.92 | 324941.56 | 77423.04 | 35858.44
56 | 35858.44 | 7315.72 | 7076.66 | 239.06 | 332018.22 | 77662.1 | 28781.78
57 | 28781.78 | 7315.72 | 7123.84 | 191.88 | 339142.06 | 77853.98 | 21657.94
58 | 21657.94 | 7315.72 | 7171.33 | 144.39 | 346313.39 | 77998.37 | 14486.61
59 | 14486.61 | 7315.72 | 7219.14 | 96.58 | 353532.53 | 78094.95 | 7267.47
60 | 7267.47 | 7315.72 | 7267.27 | 48.45 | 360799.8 | 78143.4 | 0.2
61 | 0.2 | 7315.72 | 7315.72 | 0 | 368115.52 | 78143.4 | -7315.52

## P1 Income
End of Year | Online Sales | Increased Price | Increased Sales | Total
0 | 4000000 | 0 | 400000 | 4400000
1 | 4400000 | 200000 | 440000 | 5040000
2 | 5040000 | 220000 | 504000 | 5764000
3 | 5764000 | 252000 | 576400 | 6592400
4 | 6592400 | 288200 | 659240 | 7539840
5 | 7539840 | 329620 | 753984 | 8623444
6 | 8623444 | 376992 | 862344.4 | 9862780.4
7 | 9862780.4 | 431172.2 | 986278.04 | 11280230.64
8 | 11280230.64 | 493139.02 | 1128023.064 | 12901392.724
9 | 12901392.724 | 564011.532 | 1290139.2724 | 14755543.5284
10 | 14755543.5284 | 645069.6362 | 1475554.3528 | 16876167.5174
Increased Sales / yr | 10%
Increased Price / yr | 5%

## P1 Expenses
End of Year |  | 0 |  | 1 |  | 2 |  | 3 |  | 4 |  | 5
Increases |  | Tasks | Costs | Tasks | Costs | Tasks | Costs | Tasks | Costs | Tasks | Costs | Tasks | Costs
+5% | /year | Salaries | 195000 | Salaries | 204750 | Salaries | 214987.5 | Salaries | 225736.875 | Salaries | 237023.7188 | Salaries | 248874.9047
+25% | /5 years | Tech Upgrades | 50000 | [8 empty] | Tech Upgrades | 62500
+5% | /year | Operational Costs | 10000 | Operational Costs | 10500 | Operational Costs | 11025 | Operational Costs | 11576.25 | Operational Costs | 12155.0625 | Operational Costs | 12762.8156
|  | Loan | 87788.64 | Loan | 87788.64 | Loan | 87788.64 | Loan | 87788.64 | Loan | 87788.64
|  | Temporary Hires | 145000 | Temporary Hires | 36250
|  | Training | 25040
Total |  |  | 512828.64 |  | 339288.64 |  | 313801.14 |  | 325101.765 |  | 336967.4213 |  | 324137.7203
End of Year |  | 6 |  | 7 |  | 8 |  | 9 |  | 10
Increases |  | Tasks | Costs | Tasks | Costs | Tasks | Costs | Tasks | Costs | Tasks | Costs
+5% | /year | Salaries | 261318.6499 | Salaries | 274384.5824 | Salaries | 288103.8115 | Salaries | 302509.0021 | Salaries | 317634.4522
+25% | /5 years | [8 empty] | Tech Upgrades | 78125
+5% | /year | Operational Costs | 13400.9564 | Operational Costs | 14071.0042 | Operational Costs | 14774.5544 | Operational Costs | 15513.2822 | Operational Costs | 16288.9463
Total |  |  | 274719.6063 |  | 288455.5866 |  | 302878.366 |  | 318022.2843 |  | 412048.3985

## P1 Cash Flow
End of year | Income | Loan | Expenses | Net Cash Flow
0 | 4400000 | 360800 | 512828.64 | 4247971.36
1 | 5040000 |  | 339288.64 | 4700711.36
2 | 5764000 |  | 313801.14 | 5450198.86
3 | 6592400 |  | 325101.765 | 6267298.235
4 | 7539840 |  | 336967.4213 | 7202872.5788
5 | 8623444 |  | 324137.7203 | 8299306.2797
6 | 9862780.4 |  | 274719.6063 | 9588060.7937
7 | 11280230.64 |  | 288455.5866 | 10991775.0534
8 | 12901392.724 |  | 302878.366 | 12598514.358
9 | 14755543.5284 |  | 318022.2843 | 14437521.2441
10 | 16876167.5174 |  | 412048.3985 | 16464119.119

## P1 Present Worth
End of Year | Cash flow value | (P/F,i,n) | Present Worth Cash Flow
0 | 4247971.36 | -1 | 4247971.36
1 | 4700711.36 | -0.95238 | 4476867.9619
2 | 5450198.86 | -0.90703 | 4943491.0295
3 | 6267298.235 | -0.86384 | 5413927.8566
4 | 7202872.5788 | -0.8227 | 5925821.0961
5 | 8299306.2797 | -0.78353 | 6502723.6337
6 | 9588060.7937 | -0.74622 | 7154758.5881
7 | 10991775.0534 | -0.71068 | 7811649.3154
8 | 12598514.358 | -0.67684 | 8527170.4206
9 | 14437521.2441 | -0.64461 | 9306554.922
10 | 16464119.119 | -0.61391 | 10107540.935
Rate | 0.05
Total |  |  | 74418477.119