## Proposal 2 WBS
Task ID | Task | Resource | Dependencies | Number of Resources | Duration (hrs) | Cost | Subtotal
1 | PHASE-1 | [5 empty] | 6450
1 | Project Initiation |  |  |  |  | 6450
1.1 | Project Kickoff Meeting | Project Manager | - | 1 | 10 | 1500
1.2 | Project Planning | Project Manager & Business Analyst | 1.1 | 2 | 15 | 3450
1.3 | Contract Negotiation | Project Manager | 1.1,1.2 | 1 | 10 | 1500
PHASE-1 Complete
6600
2 | PHASE - 2 Requirement Analysis |  |  |  |  | 6600
2.1 | Gather Business Requirements | Business Analyst & Stakeholders | 1.3 | 2 | 20 | 1600
2.2 | Define Functional Requirements | Business Analyst & IT Manager | 2.1 | 2 | 15 | 3000
2.3 | Define Non-Functional Requirements | Business Analyst | 2.1,2.2 | 1 | 25 | 2000
PHASE-2 Complete
3 | PHASE - 3 Platform Optimization | [5 empty] | 54050
3.1 | User Experience Enhancement |  |  |  |  | 7400
3.1.1 | Conduct User Surveys | Front-end Developers | 2.1 | 1 | 15 | 1125
3.1.2 | Analyze User Feedback | Front-end Developers | 3.1.1 | 1 | 15 | 1125
3.1.3 | Design User Personas | Sr Developer | 3.1.1.3.1.2 | 1 | 20 | 1700
3.1.4 | Wireframing and Prototyping | Sr Developer | 3.1.3 | 1 | 20 | 1700
3.1.5 | User Interface Design | UX Designer | 3.1.3,3.1.4 | 1 | 25 | 1750
3.2 | Interface Design |  |  |  |  | 3850
3.2.1 | Design Interface Layout | UX Designer | 3.1.3,3.1.5 | 1 | 15 | 1050
3.2.2 | Implement Responsive Design | UX Designer | 3.2.1 | 1 | 20 | 1400
3.2.3 | Visual Design Enhancement | UX Designer | 3.2.1,3.2.3 | 1 | 20 | 1400
3.3 | Scalability Improvement |  |  |  |  | 5450
3.3.1 | Performance Testing | Tester I | 3.2.3 | 1 | 15 | 1050
3.3.2 | Load Testing | Tester I | 3.3.1 | 1 | 20 | 1400
3.3.3 | Scalability Analysis | Back-end Developer | 3.3.1,3.3.2 | 1 | 15 | 1125
3.3.4 | Implement Scalability Solutions | Back-end Developer | 3.3.1,3.3.2,3.3.3 | 1 | 25 | 1875
3.4 | Customer-Centric Features Integration |  |  |  |  | 10400
3.4.1 | Feature Prioritization | Front-end Developers | 3.1.2,3.2.1 | 1 | 20 | 1500
3.4.2 | Development of Customer-Centric Features | Front-end Developers | 3.4.1 | 2 | 50 | 7500
3.4.3 | Testing and Feedback Incorporation | Tester II | 3.3.4,3.1.2,3.1.1,3.1.5 | 1 | 20 | 1400
3.5 | Integration of Salesforce |  | 3.3.4,3.4.1,3.4.2 |  |  | 9400
3.5.1 | Requirement Gathering for Integration | Integration Specialist | 3.4.2 | 2 | 30 | 5100
3.5.2 | Configuration and Customization | Saleforce Admins | 3.5.1 | 1 | 20 | 1300
3.5.3 | Data Migration and Synchronization | Saleforce Admins | 3.5.1,3.5.2 | 1 | 20 | 1300
3.5.4 | Testing and User Acceptance | Integration Specialist | 3.5.1,3.5.2,3.5.3 | 1 | 20 | 1700
3.6 | Integration of Payment Gateways |  |  |  |  | 9100
3.6.1 | Research and Selection of Payment Gateways | Back-end Developer | 2.1,3.1.1,3.1.2 | 2 | 30 | 2250
3.6.2 | Integration Planning | Back-end Developer | 3.6.1 | 2 | 30 | 2250
3.6.3 | Payment Gateway Implementation | Back-end Developer | 2.2,3.1.3,3.6.2 | 2 | 40 | 3000
3.6.4 | Testing Payment Processes | Payment Gateway Specialist | 3.6.3 | 2 | 20 | 1600
3.7 | Technology Upgrade |  |  |  |  | 8450
3.7.1 | Assess Current Technology Stack | IT Manager | 2.1 | 1 | 20 | 2400
3.7.2 | Research and Selection of New Technologies | IT Manager | 3.7.1 | 1 | 20 | 2400
3.7.3 | Implementation of Technology Upgrade | Front-end Developers | 3.7.2 | 1 | 30 | 2250
3.7.4 | Testing and Debugging | Tester I | 3.6.4,3.7.4 | 1 | 20 | 1400
PHASE-3 Complete
4 | PHASE - 4 Resource Allocation | [5 empty] | 8100
4.1 | Team Formation |  |  |  |  | 2200
4.1.1 | Identify Team Members | HR | 1.2,2.1 | 1 | 10 | 700
4.1.2 | Assign Roles and Responsibilities | Project Manager | 4.1.1 | 1 | 10 | 1500
4.2 | Setup Infrastructure |  |  |  |  | 3800
4.2.1 | Procure Necessary Hardware and Software | IT Manager | 2.3 | 1 | 20 | 2400
4.2.2 | Setup Development and Testing Environments | Tester I | 2.3 | 1 | 20 | 1400
4.3 | Onboarding and Training |  |  |  |  | 2100
4.3.1 | Orientation to Project Goals and Objectives | HR | 1.1,1.2 | 1 | 10 | 700
4.3.2 | Training on Tools and Technologies | HR | 4.3.1 | 1 | 20 | 1400
PHASE-4 Complete
13500
5 | PHASE - 5 Project Management |  |  |  |  | 13500
5.1 | Task Scheduling | Project Manager | 4.3 | 1 | 15 | 2250
5.2 | Progress Monitoring | Project Manager | 5.1 | 1 | 20 | 3000
5.3 | Issue Tracking and Resolution | Project Manager | 2,3,4 | 1 | 20 | 3000
5.4 | Stakeholder Communication | Project Manager | 2.1 | 1 | 15 | 2250
5.5 | Risk Management | Project Manager | 1,2,3,4,5.1,5.2,5.3,5.4 | 1 | 20 | 3000
PHASE-5 Complete
6300
6 | PHASE- 6 Quality Assurance |  |  |  |  | 6300
6.1 | Test Plan Development | Tester I | 5.1,5.2 | 1 | 15 | 1050
6.2 | Test Case Creation | Tester I | 6.1 | 1 | 20 | 1400
6.3 | Functional Testing | Tester I | 6.1,6.2 | 1 | 20 | 1400
6.4 | Performance Testing | Tester I | 6.1,6.2,6.3 | 1 | 20 | 1400
6.5 | User Acceptance Testing | Tester I | 6.1,6.2,6.3,6.4 | 1 | 15 | 1050
PHASE-6 Complete
10200
7 | PHASE - 7 Deployment and Post-Deployment Support |  |  |  |  | 10200
7.1 | Deployment Planning | DevOps Engineer | 6 | 2 | 20 | 2000
7.2 | Deployment Execution | DevOps Engineer | 7.1 | 2 | 30 | 3000
7.3 | Post-Deployment Monitoring | Project Manager | 7.1,7.2 | 1 | 20 | 3000
7.4 | Bug Fixing and Maintenance | Support Staff | 7.3 | 2 | 40 | 2200
PHASE-7 Complete
8 | Project Complete
TOTAL HOURS |  |  |  |  | 1090
TOTAL COST | [6 empty] | 105200

## Proposal 2 Resources
Resource | Hourly | FTE
Project Manager | 150 | 312000
IT Manager | 120 | 249600
HR | 70 | 145600
Business Analyst | 80 | 166400
Sr Developer | 85 | 176800
UX Designer | 70 | 145600
Back-end Developer | 75 | 156000
Front-end Developer | 75 | 156000
Tester I | 70 | 145600
Tester II | 70 | 145600
Intergration Specialist | 85 | 176800
Saleforce Admins | 65 | 135200
Payment Gateway Specialist | 80 | 166400
DevOps Engineer | 100 | 208000
Support Staff | 55 | 114400

## P2 Loan
Loan Amount: | 246000
Interest Rate: | 8%
Loan Payment Period (years): | 5
End of Year | Loan Payment | Principal Payment | Interest payment
1 | 61612.2878 | 41932.2878 | 8416
2 | 61612.2878 | 45286.8708 | 6981.4385
3 | 61612.2878 | 48909.8205 | 5432.112
4 | 61612.2878 | 52822.6062 | 3758.8395
5 | 61612.2878 | 57048.4147 | 1951.7051
6 | 61612.2878 | 48909.8205 | 5432.112
7 | 61612.2878 | 52822.6062 | 3758.8395
8 | 61612.2878 | 57048.4147 | 1951.7051
9 | 61612.2878 | 48909.8205 | 5432.112
10 | 61612.2878 | 52822.6062 | 3758.8395

## P2 Income
End of Year | Online Sales | Increased Price | Increased Sales | Total
0 | 4000000 | 0 | 400000 | 4400000
1 | 4400000 | 200000 | 440000 | 5040000
2 | 5040000 | 220000 | 504000 | 5764000
3 | 5764000 | 252000 | 576400 | 6592400
4 | 6592400 | 288200 | 659240 | 7539840
5 | 7539840 | 329620 | 753984 | 8623444
6 | 8623444 | 376992 | 862344.4 | 9862780.4
7 | 9862780.4 | 431172.2 | 986278.04 | 11280230.64
8 | 11280230.64 | 493139.02 | 1128023.064 | 12901392.724
9 | 12901392.724 | 564011.532 | 1290139.2724 | 14755543.5284
10 | 14755543.5284 | 645069.6362 | 1475554.3528 | 16876167.5174
Increased Sales / yr | 10%
Increased Price / yr | 5%

## P2 Expense
End of Year | 0 |  | 1 |  | 2 |  | 3 |  | 4 |  | 5
Increases | Tasks | Costs | Tasks | Costs | Tasks | Costs | Tasks | Costs | Tasks | Costs | Tasks | Costs
5% /1year | Salaries (Development) | $50,000 | Salaries (Development) | $52,500 | Salaries (Development) | $55,125 | Salaries (Development) | $57,881 | Salaries (Development) | $60,775 | Salaries (Development) | $63,814
5% /1year | Salaries (Testing) | $8,000 | Salaries (Testing) | $8,400 | Salaries (Testing) | $8,820 | Salaries (Testing) | $9,261 | Salaries (Testing) | $9,724 | Salaries (Testing) | $10,210
| Resource Costs | $16,000 | Resource Costs | $16,000 | Resource Costs | $16,000 | Resource Costs | $16,000 | Resource Costs | $16,000 | Resource Costs | $16,000
25% /5years | Technology Upgrades | $50,000 | Technology Upgrades | $0 | Technology Upgrades | $0 | Technology Upgrades | $0 | Technology Upgrades | $0 | Technology Upgrades | $62,500
| Buffer Expense | $5,000 | Buffer Expense | $5,000 | Buffer Expense | $5,000 | Buffer Expense | $5,000 | Buffer Expense | $5,000 | Buffer Expense | $5,000
5% /1year | Post-implementation Support | $10,000 | Post-implementation Support | $10,500 | Post-implementation Support | $11,025 | Post-implementation Support | $11,576 | Post-implementation Support | $12,155 | Post-implementation Support | $12,763
| Licensing Fees | $5,000 | Licensing Fees | $5,000 | Licensing Fees | $5,000 | Licensing Fees | $5,000 | Licensing Fees | $5,000 | Licensing Fees | $5,000
5% /1year | Contingency Budget | $10,000 | Contingency Budget | $10,500 | Contingency Budget | $11,025 | Contingency Budget | $11,576 | Contingency Budget | $12,155 | Contingency Budget | $12,763
Total |  | $154,000 |  | $107,900 |  | $111,995 |  | $116,294 |  | $120,809 |  | $188,050
End of Year | 6 |  | 7 |  | 8 |  | 9 |  | 10
Increases | Tasks | Costs | Tasks | Costs | Tasks | Costs | Tasks | Costs | Tasks | Costs
5% /1year | Salaries (Development) | $67,005 | Salaries (Development) | $70,355 | Salaries (Development) | $73,873 | Salaries (Development) | $77,566 | Salaries (Development) | $81,445
5% /1year | Salaries (Testing) | $10,721 | Salaries (Testing) | $11,257 | Salaries (Testing) | $11,820 | Salaries (Testing) | $12,411 | Salaries (Testing) | $13,031
| Resource Costs | $16,000 | Resource Costs | $16,000 | Resource Costs | $16,000 | Resource Costs | $16,000 | Resource Costs | $16,000
25% /5years | Technology Upgrades | $0 | Technology Upgrades | $0 | Technology Upgrades | $0 | Technology Upgrades | $0 | Technology Upgrades | $78,125
| Buffer Expense | $5,000 | Buffer Expense | $5,000 | Buffer Expense | $5,000 | Buffer Expense | $5,000 | Buffer Expense | $5,000
5% /1year | Post-implementation Support | $13,401 | Post-implementation Support | $14,071 | Post-implementation Support | $14,775 | Post-implementation Support | $15,513 | Post-implementation Support | $16,289
| Licensing Fees | $5,000 | Licensing Fees | $5,000 | Licensing Fees | $5,000 | Licensing Fees | $5,000 | Licensing Fees | $5,000
5% /1year | Contingency Budget | $13,401 | Contingency Budget | $14,071 | Contingency Budget | $14,775 | Contingency Budget | $15,513 | Contingency Budget | $16,289
Total |  | $130,528 |  | $135,754 |  | $141,243 |  | $147,003 |  | $231,179

## P2 Cash Flow
End of year | Income | Expenses | Net Cash Flow
0 | 4400000 | $154,000 | 4246000
1 | 5040000 | $107,900 | 4932100
2 | 5764000 | $111,995 | 5652005
3 | 6592400 | $116,294 | 6476106
4 | 7539840 | $120,809 | 7419031
5 | 8623444 | $188,050 | 8435394
6 | 9862780.4 | $130,528 | 9732252.4
7 | 11280230.64 | $135,754 | 11144476.64
8 | 12901392.724 | $141,243 | 12760149.724
9 | 14755543.5284 | $147,003 | 14608540.5284
10 | 16876167.5174 | $231,179 | 16644988.5174

## P2 Present Worth
End of Year | Cash flow value | (P/F,i,n) | Present Worth Cash Flow
0 | 4246000 | -1 | 4246000
1 | 4932100 | -0.95238 | 4697238.0952
2 | 5652005 | -0.90703 | 5126535.1474
3 | 6476106 | -0.86384 | 5594303.8549
4 | 7419031 | -0.8227 | 6103655.1643
5 | 8435394 | -0.78353 | 6609351.9235
6 | 9732252.4 | -0.74622 | 7262356.5848
7 | 11144476.64 | -0.71068 | 7920171.4821
8 | 12760149.724 | -0.67684 | 8636571.5986
9 | 14608540.5284 | -0.64461 | 9416795.4775
10 | 16644988.5174 | -0.61391 | 10218579.0559
Rate | 5%
Total |  |  | 75831558.3842