## Proposal 1
Task ID | Task | Resource | Dependencies | Number of Resources | Duration (hrs) | Cost | Subtotal | Actual Weeks
1 | Phase 1: Pre-development activities | [5 empty] | 16912
1.1 | System requirements analysis |  |  |  |  | 2880 |  | 2.5
1.1.1 | Gather UI/UX requirements | Project Manager | - | 1 | 10 | 480
1.1.2 | Gather front-end development requirements | Project Manager | - | 1 | 10 | 480
1.1.3 | Gather database requirements | Project Manager | - | 1 | 10 | 480
1.1.4 | Gather service integration requirements | Project Manager | - | 1 | 10 | 480
1.1.5 | Finalize requirements | Project Manager | 1.1.1, 1.1.2, 1.1.3, 1.1.4 | 1 | 20 | 960
1.2 | Team Expansion |  |  |  |  | 7752 |  | 5
1.2.1 | Determine team requirements | HR Representative | 1.1.5 | 1 | 20 | 760
1.2.2 | Create job descriptions for open positions | HR Representative | 1.2.1 | 1 | 20 | 760
1.2.3 | Accept applications for new open positions | HR Representative | 1.2.2 | 1 | 40 | 1520
1.2.4 | Interview applicants - first round | HR Representative | 1.2.3 | 1 | 40 | 1520
1.2.5 | Interview applicants - second round | HR Representative | 1.2.4 | 1 | 40 | 1520
1.2.6 | Finalize offers | HR Representative | 1.2.5 | 1 | 20 | 760
1.2.7 | Onboard new hires | HR Representative | 1.2.6 | 1 | 24 | 912
1.3 | Training |  |  |  |  | 6280 |  | 1
1.3.1 | Training for existing employees | Technical Trainer, Sr. Developer, Jr. Developer I, Jr. Developer II | 1.2.7 | 4 | 40 | 6280
1.4 | Phase 1: Complete
2 | Phase 2: UI/UX Site Design | [5 empty] | 24160
2.1 | Create wireframes |  |  |  |  | 6080 |  | 4
2.1.1 | Develop wireframes for site designs | UI Designer | 1.3.1 | 1 | 80 | 3200
2.1.2 | Wireframe approvals (first round) | UI Designer | 2.1.1 | 1 | 16 | 640
2.1.3 | Wireframe updates | UI Designer | 2.1.2 | 1 | 40 | 1600
2.1.4 | Wireframe approvals (second round) | UI Designer | 2.1.3 | 1 | 16 | 640
2.2 | Develop site pages |  |  |  |  | 14400 |  | 9
2.2.1 | Develop product catalog page | UI Designer | 2.1.3 | 1 | 60 | 2400
2.2.2 | Develop individual product pages | UI Designer | 2.1.3 | 1 | 60 | 2400
2.2.3 | Develop customer review sections | UI Designer | 2.1.3 | 1 | 60 | 2400
2.2.4 | Develop customer account pages | UI Designer | 2.1.3 | 1 | 60 | 2400
2.2.5 | Develop cart and checkout pages | UI Designer | 2.1.3 | 1 | 60 | 2400
2.2.6 | Develop informational pages | UI Designer | 2.1.3 | 1 | 60 | 2400
2.3 | UI/UX Approvals |  |  |  |  | 3680 |  | 2.5
2.3.1 | UI/UX approvals (first round) | UI Designer | 2.2.1, 2.2.2, 2.2.3, 2.2.4, 2.2.5, 2.2.6 | 1 | 16 | 640
2.3.2 | UI/UX revisions | UI Designer | 2.3.1 | 1 | 60 | 2400
2.3.3 | UI/UX final approval | UI Designer | 2.3.2 | 1 | 16 | 640
2.4 | Phase 2: Complete
3 | Phase 3: Web application development | [5 empty] | 62856
3.1 | Develop product subsystem |  |  |  |  | 7440 |  | 2
3.1.1 | Build data schema for products | Sr. Developer | 1.1.5, 1.2.7 | 1 | 20 | 1200
3.1.2 | Build interface for product data | Sr. Developer | 3.1.1 | 1 | 60 | 3600
3.1.3 | Build API endpoints for products | Jr. Developer I | 3.1.1 | 1 | 40 | 1320
3.1.4 | Build business logic for products | Jr. Developer II | 3.1.1 | 1 | 40 | 1320
3.2 | Develop customer subsystem |  |  |  |  | 7440 |  | 3
3.2.1 | Build data schema for customer info | Sr. Developer | 1.1.5, 1.2.7 | 1 | 20 | 1200
3.2.2 | Build interface for customer data | Sr. Developer | 3.2.1 | 1 | 60 | 3600
3.2.3 | Build API endpoints for customer info | Jr. Developer I | 3.2.1 | 1 | 40 | 1320
3.2.4 | Build business logic for customer info | Jr. Developer II | 3.2.1 | 1 | 40 | 1320
3.3 | Develop pricing subsystem |  |  |  |  | 7440 |  | 3
3.3.1 | Build pricing data schema | Sr. Developer | 1.1.5, 1.2.7 | 1 | 20 | 1200
3.3.2 | Build interfacec for pricing data | Sr. Developer | 3.3.1 | 1 | 60 | 3600
3.3.3 | Build API endpoints for pricing | Jr. Developer I | 3.3.1 | 1 | 40 | 1320
3.3.4 | Build business logic for pricing | Jr. Developer II | 3.3.1 | 1 | 40 | 1320
3.4 | Develop transaction subsystem |  |  |  |  | 7440 |  | 3
3.4.1 | Build transaction data schema | Sr. Developer | 1.1.5, 1.2.7 | 1 | 20 | 1200
3.4.2 | Build interface for transaction data | Sr. Developer | 3.4.1 | 1 | 60 | 3600
3.4.3 | Build API endpoints for transactions | Jr. Developer I | 3.4.1 | 1 | 40 | 1320
3.4.4 | Build business logic for transactions | Jr. Developer II | 3.4.1 | 1 | 40 | 1320
3.5 | Develop product review subsystem |  |  |  |  | 7440 |  | 3
3.5.1 | Build review data schema | Sr. Developer | 1.1.5, 1.2.7 | 1 | 20 | 1200
3.5.2 | Build interface for review data | Sr. Developer | 3.5.1 | 1 | 60 | 3600
3.5.3 | Build API endpoints for product reviews | Jr. Developer I | 3.5.1 | 1 | 40 | 1320
3.5.4 | Build business logic for product reviews | Jr. Developer II | 3.5.1 | 1 | 40 | 1320
3.6 | Develop inventory management subsystem |  |  |  |  | 7440 |  | 3
3.6.1 | Build inventory management schema | Sr. Developer | 1.1.5, 1.2.7 | 1 | 20 | 1200
3.6.2 | Build interface for inventory management data | Sr. Developer | 3.6.1 | 1 | 60 | 3600
3.6.3 | Build API endpoints for inventory management | Jr. Developer I | 3.6.1 | 1 | 40 | 1320
3.6.4 | Build business logic for inventory management | Jr. Developer II | 3.6.1 | 1 | 40 | 1320
3.7 | Develop tax and shipping subsystem |  |  |  |  | 7440 |  | 3
3.7.1 | Build shipping and tax schema | Sr. Developer | 1.1.5, 1.2.7 | 1 | 20 | 1200
3.7.2 | Build interface for shipping and tax data | Sr. Developer | 3.7.1 | 1 | 60 | 3600
3.7.3 | Build API endpoints for shipping and tax processing | Jr. Developer I | 3.7.1 | 1 | 40 | 1320
3.7.4 | Build business logic for shipping and tax processing | Jr. Developer II | 3.7.1 | 1 | 40 | 1320
3.8 | Subsystem testing |  |  |  |  | 6600 |  | 2.5
3.8.1 | Integration testing | Tester I, Tester II | 3.1.1, 3.1.2, 3.1.3, 3.1.4, 3.2.1, 3.2.2, 3.2.3, 3.2.4, 3.3.1, 3.3.2, 3.3.3, 3.3.4, 3.4.1, 3.4.2, 3.4.3, 3.4.4, 3.5.1, 3.5.2, 3.5.3, 3.5.4, 3.6.1, 3.6.2, 3.6.3, 3.6.4, 3.7.1, 3.7.2, 3.7.3, 3.7.4 | 2 | 60 | 3960
3.8.2 | Acceptence testing | Tester I, Tester II | 3.8.1 | 2 | 40 | 2640
3.9 | System Approvals |  |  |  |  | 4176 |  | 2
3.9.1 | System approvals (first round) | Project Manager | 3.8.1, 3.8.2 | 1 | 16 | 768
3.9.2 | System revisions | Jr. Developer I, Jr. Developer II | 3.9.1 | 2 | 40 | 2640
3.9.3 | System final approval | Project Manager | 3.9.2 | 1 | 16 | 768
3.10 | Phase 3: Complete
4 | Phase 4: Deployment | [5 empty] | 1008
4.1 | Infrastructure |  |  |  |  | 800 |  | 0.5
4.1.1 | Build infrastructure | Infrastructure | 1.1.5 | 1 | 10 | 400
4.1.2 | Install required services | Infrastructure | 4.1.2 | 1 | 10 | 400
4.2 | Deploy website to infrastructure |  |  |  |  | 208 |  | 0.1
4.2.1 | Configure deployment pipelines | Dev Ops | 4.1.2 | 1 | 2 | 104
4.2.2 | Deploy website | Dev Ops | 4.2.1, 3.9.3 | 1 | 2 | 104
4.3 | Phase 4: Complete
5 | Phase 5: SalesForce integration | [5 empty] | 13104
5.1 | Develop data adapters |  |  |  |  | 4800 |  | 2
5.1.1 | Map customer data to SalesForce data | Sr. Developer | 3.2.4 | 1 | 40 | 2400
5.1.2 | Develop data conversion adapter | Sr. Developer | 5.1.1 | 1 | 40 | 2400
5.2 | Service integration |  |  |  |  | 5040 |  | 1
5.2.1 | Develop data egress to SalesForce | Jr. Developer I | 5.1.2 | 1 | 40 | 1320
5.2.2 | Develop data ingress from SalesForce | Jr. Developer II | 5.1.2 | 1 | 40 | 1320
5.2.3 | Develop data sync service | Sr. Developer | 5.1.2 | 1 | 40 | 2400
5.3 | SalesForce integration testing |  |  |  |  | 3056 |  | 1
5.3.1 | Test data egress | Tester I, Tester II | 5.2.3 | 2 | 20 | 1320
5.3.2 | Test data ingress | Tester I, Tester II | 5.3.1 | 2 | 20 | 1320
5.4 | SalesForce integration deployment |  |  |  |  | 208 |  | 0.1
5.4.1 | Cut-over to production customer data | Dev Ops | 4.2.2 | 1 | 2 | 104
5.4.2 | Cut-over to production SalesForce instance | Dev Ops | 5.3.2 | 1 | 2 | 104
5.5 | Phase 5: Complete
6 | Project Complete
TOTAL DURATION (CUMULATIVE HOURS) |  |  |  |  | 2768
ACTUAL DURATION (WEEKS) |  |  |  |  | 54
TOTAL COST | [6 empty] | 118040
Note on J1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: I estimated what the total of weeks of work (over lapping tasks, considering resources, and dependencies). I might wrap this into the WBS or hide the column.

## Proposal 1 Resources
Resource | Hourly | Weekly | FTE
Project Manager | 48 | 1923 | 100000
Dev Ops | 52 | 2115 | 110000
Sr. Developer | 60 | 2403 | 125000
Jr. Developer I | 33 | 1346 | 70000
Jr. Developer II | 33 | 1346 | 70000
UI Developer | 40 | 1634 | 85000
Infrastructure | 40 | 1634 | 85000
HR Representative | 38 | 1538 | 80000
Technical Trainer | 31 | 1250 | 65000
Tester I | 33 | 1346 | 70000
Tester II | 33 | 1346 | 70000

## Proposal 2
Task ID | Task | Resource | Dependencies | Number of Resources | Duration (hrs) | Cost | Subtotal
1 | PHASE-1 | [5 empty] | 6450
1 | Project Initiation |  |  |  |  | 6450
1.1 | Project Kickoff Meeting | Project Manager | - | 1 | 10 | 1500
1.2 | Project Planning | Project Manager & Business Analyst | 1.1 | 2 | 15 | 3450
1.3 | Contract Negotiation | Project Manager | 1.1,1.2 | 1 | 10 | 1500
PHASE-1 Complete
6600
2 | PHASE - 2 Requirement Analysis |  |  |  |  | 6600
2.1 | Gather Business Requirements | Business Analyst & Stakeholders | 1.3 | 2 | 20 | 1600
2.2 | Define Functional Requirements | Business Analyst & IT Manager | 2.1 | 2 | 15 | 3000
2.3 | Define Non-Functional Requirements | Business Analyst | 2.1,2.2 | 1 | 25 | 2000
PHASE-2 Complete
3 | PHASE - 3 Platform Optimization | [5 empty] | 54050
3.1 | User Experience Enhancement |  |  |  |  | 7400
3.1.1 | Conduct User Surveys | Front-end Developers | 2.1 | 1 | 15 | 1125
3.1.2 | Analyze User Feedback | Front-end Developers | 3.1.1 | 1 | 15 | 1125
3.1.3 | Design User Personas | Sr Developer | 3.1.1.3.1.2 | 1 | 20 | 1700
3.1.4 | Wireframing and Prototyping | Sr Developer | 3.1.3 | 1 | 20 | 1700
3.1.5 | User Interface Design | UX Designer | 3.1.3,3.1.4 | 1 | 25 | 1750
3.2 | Interface Design |  |  |  |  | 3850
3.2.1 | Design Interface Layout | UX Designer | 3.1.3,3.1.5 | 1 | 15 | 1050
3.2.2 | Implement Responsive Design | UX Designer | 3.2.1 | 1 | 20 | 1400
3.2.3 | Visual Design Enhancement | UX Designer | 3.2.1,3.2.3 | 1 | 20 | 1400
3.3 | Scalability Improvement |  |  |  |  | 5450
3.3.1 | Performance Testing | Tester I | 3.2.3 | 1 | 15 | 1050
3.3.2 | Load Testing | Tester I | 3.3.1 | 1 | 20 | 1400
3.3.3 | Scalability Analysis | Back-end Developer | 3.3.1,3.3.2 | 1 | 15 | 1125
3.3.4 | Implement Scalability Solutions | Back-end Developer | 3.3.1,3.3.2,3.3.3 | 1 | 25 | 1875
3.4 | Customer-Centric Features Integration |  |  |  |  | 10400
3.4.1 | Feature Prioritization | Front-end Developers | 3.1.2,3.2.1 | 1 | 20 | 1500
3.4.2 | Development of Customer-Centric Features | Front-end Developers | 3.4.1 | 2 | 50 | 7500
3.4.3 | Testing and Feedback Incorporation | Tester II | 3.3.4,3.1.2,3.1.1,3.1.5 | 1 | 20 | 1400
3.5 | Integration of Salesforce |  | 3.3.4,3.4.1,3.4.2 |  |  | 9400
3.5.1 | Requirement Gathering for Integration | Integration Specialist | 3.4.2 | 2 | 30 | 5100
3.5.2 | Configuration and Customization | Saleforce Admins | 3.5.1 | 1 | 20 | 1300
3.5.3 | Data Migration and Synchronization | Saleforce Admins | 3.5.1,3.5.2 | 1 | 20 | 1300
3.5.4 | Testing and User Acceptance | Integration Specialist | 3.5.1,3.5.2,3.5.3 | 1 | 20 | 1700
3.6 | Integration of Payment Gateways |  |  |  |  | 9100
3.6.1 | Research and Selection of Payment Gateways | Back-end Developer | 2.1,3.1.1,3.1.2 | 2 | 30 | 2250
3.6.2 | Integration Planning | Back-end Developer | 3.6.1 | 2 | 30 | 2250
3.6.3 | Payment Gateway Implementation | Back-end Developer | 2.2,3.1.3,3.6.2 | 2 | 40 | 3000
3.6.4 | Testing Payment Processes | Payment Gateway Specialist | 3.6.3 | 2 | 20 | 1600
3.7 | Technology Upgrade |  |  |  |  | 8450
3.7.1 | Assess Current Technology Stack | IT Manager | 2.1 | 1 | 20 | 2400
3.7.2 | Research and Selection of New Technologies | IT Manager | 3.7.1 | 1 | 20 | 2400
3.7.3 | Implementation of Technology Upgrade | Front-end Developers | 3.7.2 | 1 | 30 | 2250
3.7.4 | Testing and Debugging | Tester I | 3.6.4,3.7.4 | 1 | 20 | 1400
PHASE-3 Complete
4 | PHASE - 4 Resource Allocation | [5 empty] | 8100
4.1 | Team Formation |  |  |  |  | 2200
4.1.1 | Identify Team Members | HR | 1.2,2.1 | 1 | 10 | 700
4.1.2 | Assign Roles and Responsibilities | Project Manager | 4.1.1 | 1 | 10 | 1500
4.2 | Setup Infrastructure |  |  |  |  | 3800
4.2.1 | Procure Necessary Hardware and Software | IT Manager | 2.3 | 1 | 20 | 2400
4.2.2 | Setup Development and Testing Environments | Tester I | 2.3 | 1 | 20 | 1400
4.3 | Onboarding and Training |  |  |  |  | 2100
4.3.1 | Orientation to Project Goals and Objectives | HR | 1.1,1.2 | 1 | 10 | 700
4.3.2 | Training on Tools and Technologies | HR | 4.3.1 | 1 | 20 | 1400
PHASE-4 Complete
13500
5 | PHASE - 5 Project Management |  |  |  |  | 13500
5.1 | Task Scheduling | Project Manager | 4.3 | 1 | 15 | 2250
5.2 | Progress Monitoring | Project Manager | 5.1 | 1 | 20 | 3000
5.3 | Issue Tracking and Resolution | Project Manager | 2,3,4 | 1 | 20 | 3000
5.4 | Stakeholder Communication | Project Manager | 2.1 | 1 | 15 | 2250
5.5 | Risk Management | Project Manager | 1,2,3,4,5.1,5.2,5.3,5.4 | 1 | 20 | 3000
PHASE-5 Complete
6300
6 | PHASE- 6 Quality Assurance |  |  |  |  | 6300
6.1 | Test Plan Development | Tester I | 5.1,5.2 | 1 | 15 | 1050
6.2 | Test Case Creation | Tester I | 6.1 | 1 | 20 | 1400
6.3 | Functional Testing | Tester I | 6.1,6.2 | 1 | 20 | 1400
6.4 | Performance Testing | Tester I | 6.1,6.2,6.3 | 1 | 20 | 1400
6.5 | User Acceptance Testing | Tester I | 6.1,6.2,6.3,6.4 | 1 | 15 | 1050
PHASE-6 Complete
10200
7 | PHASE - 7 Deployment and Post-Deployment Support |  |  |  |  | 10200
7.1 | Deployment Planning | DevOps Engineer | 6 | 2 | 20 | 2000
7.2 | Deployment Execution | DevOps Engineer | 7.1 | 2 | 30 | 3000
7.3 | Post-Deployment Monitoring | Project Manager | 7.1,7.2 | 1 | 20 | 3000
7.4 | Bug Fixing and Maintenance | Support Staff | 7.3 | 2 | 40 | 2200
PHASE-7 Complete
8 | Project Complete
TOTAL HOURS |  |  |  |  | 1090
TOTAL COST | [6 empty] | 105200

## Proposal 2 Resources
Resource | Hourly | FTE
Project Manager | 150 | 312000
IT Manager | 120 | 249600
HR | 70 | 145600
Business Analyst | 80 | 166400
Sr Developer | 85 | 176800
UX Designer | 70 | 145600
Back-end Developer | 75 | 156000
Front-end Developer | 75 | 156000
Tester I | 70 | 145600
Tester II | 70 | 145600
Intergration Specialist | 85 | 176800
Saleforce Admins | 65 | 135200
Payment Gateway Specialist | 80 | 166400
DevOps Engineer | 100 | 208000
Support Staff | 55 | 114400